## Gantt Chart
ID | Type | Title | Assignee | Workstream | Points | Iteration 370 Jun 13 – Jun 19 | Iteration 371 Jun 20 – Jul 03 | Iteration 372 Jul 04 – Jul 17 | Iteration 373 Jul 18 – Jul 31 | Iteration 374 Aug 01 – Aug 14 | Iteration 375 Aug 15 – Aug 28 | Iteration 376 Aug 29 – Sep 11 | Iteration 377 Sep 12 – Sep 18 | Iteration 378 Sep 19 – Oct 02 | Iteration 379 Oct 03 – Oct 16 | Iteration 380 Oct 17 – Oct 30 | Iteration 381 Oct 31 – Nov 13 | Iteration 382 Nov 14 – Nov 27 | Iteration 383 Nov 28 – Dec 11 | Iteration 384 Dec 12 – Dec 18 | Risk / Notes
66731 | Feature | Self Service Portal - Extract Ingestion - Quality Automation (DOM) | Bonnie Bordelon | Backend | 0
66747 | Feature | Operational Portal Backend | Bonnie Bordelon | Backend | 0
68248 | User Story | {Enhancement} Edit project modal - project file location field has generic data ** Recording project file folder location | Aristides Solis | Backend | 0 | ●
68136 | Feature | AI/ML - Missing Data | Bonnie Bordelon | Backend | 0
68140 | User Story | Set up infrastructure needed to scan USCDI tables | Roberto Flores | DevOps | 5 |  | ●
68142 | User Story | Select test tables and build USCDI reference table | Cesar Trompetero | Data Engineering | 0 |  |  | ●
68143 | User Story | MappingState control tables in Azure SQL | Cesar Trompetero | Data Engineering | 0 |  |  | ●
68144 | User Story | Schema introspection notebook | Cesar Trompetero | Data Engineering | 0 |  |  | ●
68145 | User Story | Azure OpenAI connectivity test + prompt engineering | Cesar Trompetero | Data Engineering | 1 |  |  | ●
68146 | User Story | LLM mapping Notebook + Human review | Cesar Trompetero | Data Engineering | 0 |  |  | ●
68154 | User Story | Enable Purview lineage capture from Databricks | Roberto Flores | DevOps | 0 |  |  |  | ●
66746 | Feature | Cost Optimization and FinOps | Bonnie Bordelon | Backend | 0
70120 | User Story | SPIKE - Evaluate FinOps additional implemenations needed additionally to Cost Dashboards | Roberto Flores | DevOps | 3 |  |  | ●
67490 | User Story | Create Cost Dashboards with Azure Cost Explorer | Roberto Flores | DevOps | 3 |  |  | ●
66755 | Feature | Unstructured Data Support | Bonnie Bordelon | Backend | 0
67502 | User Story | Operational Portal - Display and report on errors encountered in unstructured data import and validation - frontend | Jean Arguedas | Frontend | 1 |  |  |  | ●
67503 | User Story | Operational Portal - Display and report on errors encountered in unstructured data import and validation - backend | Aristides Solis | Backend | 5 |  |  |  | ●
66750 | Feature | Governance and Security Enhancements | Bonnie Bordelon | Backend | 0
68712 | User Story | Splunk Forwarder Credentials | Roberto Flores | DevOps | 3 |  | ●
69903 | Bug | Smoke Testing Issue #1 - Customer list - Pipeline indicator colum, there is an item with incorrect label | Jose Casal | Backend | 0 | ●
70243 | User Story | IT-6: Disable Public Network Access on Log Analytics and App Insights | Roberto Flores | DevOps | 2 | ●
70244 | User Story | IT-7: Enable Defender for Containers on acrmqdpv2 | Roberto Flores | DevOps | 2 | ●
70245 | User Story | IT-8: Switch SQL Server TDE to Customer-Managed Key | Roberto Flores | DevOps | 2 | ●
70246 | User Story | IT-9: Set DisableLocalAuth on 3 App Insights Components | Roberto Flores | DevOps | 2 | ●
70248 | User Story | IT-11: Link Log Analytics Workspaces to Customer Storage for CMK | Roberto Flores | DevOps | 2 | ●
66756 | Feature | Database Backups Adapters | Bonnie Bordelon | Backend | 0
67477 | User Story | Operational Portal - Support Database Backups pipelines - Frontend | Jean Arguedas | Frontend | 2 |  |  |  | ●
67534 | User Story | Operational Portal - Support Database Backups pipelines - Backend | Aristides Solis | Backend | 3 |  |  |  | ●
70072 | User Story | SPIKE - Design technical implementation plan | Cesar Trompetero | Data Engineering | 3 | ●
66732 | Feature | Db Restore - CDC & Data Replication - Cost Optimization (DOM) | Bonnie Bordelon | Backend | 0
66749 | Feature | Monitor and Logging | Bonnie Bordelon | Backend | 0
67480 | User Story | Azure Monitor Integration | Roberto Flores | DevOps | 3 |  |  | ●
66751 | Feature | Self-service Client Portal Backend | Bonnie Bordelon | Backend | 0
67530 | User Story | Self-Service Portal - View Dataset Filelist - Backend | Aristides Solis | Backend | 1 |  | ●
67531 | User Story | Self-Service Portal - Download Detailed Upload Report PDF - Backend | Aristides Solis | Backend | 3 |  |  | ●
67057 | User Story | Self-Service Portal - Upload files from client folder to project file storage account folder - Backend | Aristides Solis | Backend | 8 |  | ●
67756 | User Story | Self-Service Portal - File uploading process real-time notifications - Backend | Aristides Solis | Backend | 3 |  |  | ●
67561 | User Story | Operational Portal - View Customer Upload Reports from Project List - backend | Aristides Solis | Backend | 2 |  |  | ●
66752 | Feature | Self-service Client Portal Frontend | Bonnie Bordelon | Backend | 0
67044 | User Story | Self-Service Portal - Login and Dataset List Page - Frontend | Jean Arguedas | Frontend | 2 |  | ●
67261 | User Story | Self-Service Portal - Import/Upload File Page - Frontend | Jean Arguedas | Frontend | 3 |  | ●
67274 | User Story | Self-Service Portal - View Dataset Filelist - Frontend | Jean Arguedas | Frontend | 2 |  | ●
67275 | User Story | Self-Service Portal - Download Detailed Import Report PDF - Frontend | Jean Arguedas | Frontend | 1 |  |  | ●
67062 | User Story | Self-Service Portal - Upload files from client folder to project file storage account folder - Frontend | Jean Arguedas | Frontend | 3 |  | ●
67753 | User Story | Self-Service Portal - Generate SAS (Shared Access Signature) token - Frontend | Jean Arguedas | Frontend | 1 |  | ●
67757 | User Story | Self-Service Portal - File uploading process real-time notifications - Frontend | Jean Arguedas | Frontend | 1 |  |  | ●
66757 | Feature | Workflow Integration | Bonnie Bordelon | Backend | 0
67471 | User Story | Enable AzCopy file upload into Azure Blob storage | Roberto Flores | DevOps | 2 |  |  |  | ●
68616 | User Story | Key-Vault-Free Container Access | Cesar Trompetero | Data Engineering | 2 | ●
68615 | User Story | Passwordless Azure SQL Access | Cesar Trompetero | Data Engineering | 2 | ●
70344 | User Story | Configure Databricks Workspace Security Groups and Enforce Privileged Account Access | Roberto Flores | DevOps | 3 |  | ●
70345 | User Story | Automate Databricks Git Folder Setup for 'etl-ingestion' Repository | Roberto Flores | DevOps | 3 |  | ●
70346 | User Story | Automate Provisioning of Databricks Orchestration Jobs from 'etl-ingestion' Workflows | Roberto Flores | DevOps | 3 |  | ●
68514 | Feature | CDC | Bonnie Bordelon | Backend | 0
68137 | User Story | Enable CDC on Source DBs | Roberto Flores | DevOps | 3 |  |  |  | ●
68138 | User Story | Configure Debezium connectors | Roberto Flores | DevOps | 5 |  |  |  | ●
68139 | User Story | Build a Databricks readStream to ingest Debezium events | Cesar Trompetero | Data Engineering | 3 |  |  |  | ●
68152 | User Story | Implementing an endpoint to receive the information to be written in the Event Hub | Aristides Solis | Backend | 2 |  |  |  | ●
68153 | User Story | Create an AZ Function to write data in the Databricks Unit Catalog | Aristides Solis | Backend | 3 |  |  |  |  | ●